## Description
Text Transformer
For people working with text data, our Text Transformer application will allow you to transform text data (e.g. change case, eliminate duplicates, etc.). The application will be available via GUI as well as remote API, thanks to which it will be possible to integrate it with existing tools.

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As a devops, I need to initialize GitHub repository for the project | 20 |  |  | • It is actually created • README.md with description is added • Every chad developer is added • Every cringe dead is invited
As a devops, I need to configure CI/CD via GitHub Actions | 18 |  |  | • It is actually configured • Every cringe dead has access to it
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps | 15 |  | 1 | o Input in the form of text and transformation sequence (names) o Input and output in JSON format o REST API allows to run any currently implemented transformation or transformation sequence
As a project manager, I need to open an environment for backlog (tbd later) | 15 |  |  | • An environment is chosen • It is actually configured • Every cringe dead has access to it
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) | 12 |  | 0.5 | o Change case of letters - set of three transformations (upper, lower, capitalize) • upper - all letters to uppercase: upper -> UPPER • lower – all letters to lowercase: Lower -> lower • capitalize – the first letter in each word to uppercase: capitalize text -> Capitalize Text • Support for letters from the English alphabet (UTF-8)
As a devops, I need to automatically generate code documentation on project build | 12 |  |  | • It is actually autogenerated • At least 1 class/interface has complete tech docs
As a developer, I need to describe app architecture in UML | 12 |  |  | • It is actually described in UML • The Decorator design pattern is used for dynamic creation of a transformer object • The side of Autobots or Decepticons is chosen
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse) | 10 |  | 0.5 | • Preserving the positions of upper and lower case letters: MirEk -> KerIm • Reverse sequence of characters • Support for all UTF-8 characters
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated | 10 |  | 1 | • conversion of integers to 1000 • conversion of floating point numbers to hundredths
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate | 10 |  | 0.5 | • Acronym expansion: for example -> e.g. • Acronym expansion: among others -> i.a. • Acronym expansion: and so on -> aso • Works regardless of case
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) | 10 |  | 0.5 | • prof. -> professor • dr -> doctor • e.g. -> for example • aso -> and so on • Preserves case: E.g. -> For example | • item 1 • item 2 • item 3 • item 4 • item 5
As a user I can convert text to Latex supported format (special characters) -> (John Smith & Sons -> John Smith \& Sons) | 2 |  | 0.5 | • & -> \& • $ -> \$
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) | 1 |  | 1 | • Convert two repeated words to one: to to -> to • Convert any number of words repeated: to to to -> to • Replace all repetitions within a text: to to after after -> to after • Works well with all UTF-8 characters
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal:
Product Backlog Item | Tasks | Labour intensity
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps |  | (for Product Backlog item)
| Learn REST API | (for task)
Set up REST server application
Define REST API JSON endpoint and schema
Implement transformation endpoint
As a devops, I need to initialize GitHub repository for the project
Task #1 to Product Backlog item
Add README.md
Invite all chad developers
Invite all cringe deads
As a devops, I need to configure CI/CD via GitHub Actions
Set up GitHub actions
As a project manager, I need to open an environment for backlog (tbd later)
Decide which tool to use
Set up the chosen one
As a devops, I need to automatically generate code documentation on project build
Generate project wiki automatically
Document some shitty Java class/interface
As a developer, I need to describe app architecture in UML
Break down application into classes and interfaces
Describe relationships between classes and interfaces using UML
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse)
Reverse the sequence
Retain the case of letters
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize)
Modify string to upper case
Modify string to lower case
Modify string to capitalist case
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated
SPIKE: how tf to do it?
Convert integers up to 1000
Convert floats to hundreths
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate
Define the predefined words
Replace words from the defined predefined list
Make the algorithm case-agnostic again
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes)
Define the predefined acronyms
Expand acronyms from the defined predefined list
Make the algorithm case-agnostic again